## Observations
Sl Name | Section | Item | Observations | Location | Category | Photo Start | Photo End | Remarks/Action By
1 | Concrete Encasing (EL+ 12.13m) | Concrete Wall | Plaster cracks were observed on wall. | Location: At EL+ 3.2m towards south-east direction. Location: At EL+ 12.13m towards South direction Location: At EL+ 3.5m towards south-west direction. | Alert | 1 | 6 | AIL
2 | Concrete Encasing (EL+ 12.13m) | Concrete Wall | Spalling of plaster was observed at few locations. | Location: At EL+ 11.28m towards west direction. | Alert | 7 |  | AIL
3 | Precast RCC Chimney Shell | Precast RCC Shell | Honeycombing was observed at certain locations. | Location: At EL+ 26m towards south direction. | Alarm | 8 |  | AIL
4 | Precast RCC Chimney Shell | Precast RCC Shell | A crack was observed on the joint mortar of two consecutive precast chimney shells. | Location: At EL+ 18.55m towards north-west direction. Location: At EL+ 17m towards north-west direction. Location: At EL+ 27.5m towards south direction. Location: At EL+ 29.4m towards south direction. Location: At EL+ 30.95m towards south direction. | Alert | 9 | 13 | AIL
5 | Precast RCC Chimney Shell | Precast RCC Shell | Hairline cracks were observed on the chimney shell at many locations. | Location: Between EL+ 12.13m to 35m towards in all directions. | Alarm | 14 | 17 | AIL
6 | Steel Structure | Gusset plate | Bolt was found to be loose between the column and gusset plate. | Location: At EL+ 12.35m towards north direction. | Alarm | 18 |  | AIL
7 | Steel Structure | Monkey Ladder | Bolt was found to be missing between the vertical and horizontal cage flat plate. | Location: At EL+ 15.23m towards south - east direction. Location: At EL+ 20.12m towards south - east direction. | Alert | 19 |  | AIL
8 | Steel Structure | Steel frame | Bracing, tie beam, gusset plate, monkey ladder cage and column were found to be corroded at many locations. | Location: Between EL+1.5m to 35m towards in all direction. | Alert | 20 | 26 | AIL
9
10

## Observation List
Observation
Plaster cracks were observed on wall.
Spalling of plaster was observed at few locations.
Honeycombing was observed at certain locations.
A crack was observed on the joint mortar of two consecutive precast chimney shells.
Hairline cracks were observed on the chimney shell at many locations.
Bolt was found to be loose between the column and gusset plate.
Bolt was found to be missing between the vertical and horizontal cage flat plate.
Bracing, tie beam, gusset plate, monkey ladder cage and column were found to be corroded at many locations.